## Scope
SSRS reports
1. There needs to be a separate module shown on the left bar specific for all SSRS reports. It is just a page to embed SSRS homepage.
All the functionalities on this page are fully depending on SSRS functionalities.
Tableau & TM1
1. In the Library module, it will cover TM1 & Tableau only. We hope when the mouse is hovered on the report’s snapshot or name,
it will show report attributes like owner, KPI, etc.
2. Favorite function will only work for reports shown in library module (TM1/Tableau),
A simpler way is preferred to show those reports because snapshot or sample report is no longer meaningful to the user.
General Functionalities
1. Report Theme
We’d better have several pre-defined report theme (background color, banner image, etc.) to allow us quickly change for different holidays and events.
Let’s say we’ll have 3 different themes first.
2. Share Reports
After user open a report, there’s a button to share the report by generating an email with a link inside as well as the report’s general information.
The link will allow other user to open our platform with the shared report directly, not shown the homepage.
3. Monitoring Users’ Actions
Same with the initial request, just want to make sure that we need to record “who click which report at what time” and other user actions.
Once it is stored in DB, there’s no need to build dashboards on web, we can analyze it later.
4. Applying Report Access
As you showed in demo, there’s a button beside each report which allows user to click to apply report access.
We hope this button could trigger an email based on a pre-defined template. The template should be able to read information of the report.
Logo design
A logo for the CHASSIS web BI portal needs to be designed as part of the project scope. The logo needs to reflect the culture of MBAFC as well as the principles and missions of CHASSIS.

## Overall plan
CHASSIS Overall user stories and schedule
|  |  | Development Sprints |  |  | QA Sprints
EPIC | User stories | Developer | Sprint 10/17 - 10/30 | Sprint 10/31 - 11/13 | Sprint 11/14 - 11/27 | Sprint 11/28 - 12/11
SSRS linkage | SSRS report module link | Miao yu
Report Library | TM1 reports | Miao yu
| Tableau dashboards | Miao yu
| Hover over functionality to show report details | Miao yu
| Favorite function for TM1 and tableau reports. | Miao yu
General functionality | 3 report themes | Miao yu, Neo
| Report sharing functionality | Miao yu, Neo
| User activity monitoring functionality | Miao yu, Neo
| Applying report access functionality | Miao yu, Neo
| Logo design | Xu Kun

## Sprint summary
Users stories to be completed in sprint 10/17-10/30
| User Story | User Category | Detailed Description | Owner
| There needs to be a separate module shown on the left bar specific for all SSRS reports. It is just a page to embed SSRS homepage. All the functionalities on this page are fully depending on SSRS functionalities. | Web dev | 在左侧的导航栏添加一个SSRS按钮，点击之后跳转到SSRS页面，在SSRS模块主页添加和其他模块主页相同的导航栏，点击可以跳转到其他模块，实现SSRS和不同模块之间的切换 | Miao Yu
| In the Library module, it will cover TM1 reports | Web dev | 在左侧的导航栏点击library按钮之后，右侧会显示所有的包含TM１和Tableau的报告，可以通过界面内的筛选器选择查看TM１报告 | Miao Yu
| In the Library module, it will cover Tableau reports | Web dev | 在左侧的导航栏点击library按钮之后，右侧会显示所有的包含TM１和Tableau的报告，可以通过界面内的筛选器选择查看Tableau报告 | Miao Yu
| Hover over functionality to show report details. We hope when the mouse is hovered on the report’s snapshot or name, it will show report attributes like owner, KPI, etc. | Web dev | 鼠标hover（click还是hover功能待定）报告缩略图之后会弹出一个提示框显示报告的所有详细信息，包括名称，所有者，KPI等信息，此时提示框外点击无效，点击提示框右上角可关闭提示框 | Miao Yu
| Favorite function will only work for reports shown in library module (TM1/Tableau), A simpler way is preferred to show those reports because snapshot or sample report is no longer meaningful to the user. | Web dev | 只有在library模块中的报告可以添加进favourite模块中，所以只能收藏TM1和Tableau报告，在favourite模块中的报告默认以列表形式显示，点击切换按钮可以切换为缩略图模式 | Miao Yu